## Client
Full Fucntions | Arindam Comment | Client Comment | Testing Comment
Client Login | Done |  | all okay
Client Bio a) Client Bio b) Picture Upload c) View Public Profile d) Gender e) Payment Method f) Settings i) Change Password ii) Mobile Verification g) Reviews | Done Properly. a) Done b) Done c) Done d) Done e) Done (using Luhn Algorithm) f) -> i) Done ii) Temporary Done without OTP functionality g) Done Note: Can I remove Gender,Payment, Settings,Review from Logout menu ?? As it is all can see in Client Bio page together though all is different page.
Verification Email / SMS | Not done fully but sometimes you can get mail in your spam. SMS gateway needed. | after configure final server will do it
Post Task (Project) | Done. Note: I have set Continent and Country data set but maybe later we have to set more proper data here. Budget calculation removed now as per Madam. |  | all okay
Upcoming Project a) Project Listing b) Edit project c) Project Details d) Project Details - Sort By Status e) Project Details - Filter | a) Done. b) Done c) Done d) Not Done (after all functionality is done) e) Not Done (after all functionality is done) Note: Is this comment section is needed in Project Details page. ?? |  | partly done
Project Deatils a) Review b) Make offer (checkbox) | a) Done.Showing those freelancer are submitted proposal will show here. b) Clicking the checkbox beside the freelancer name will send make offer to freelancer. Freelancer can see as a notification |  | Done
Search Freelancer a) All freelancer is showing b) Make offer can done from here also | a) Done b) Done |  | all okay
Message a) When any freelancer accept the Make offer notification he will arrive in the message page and both can talk. | a) Done |  | all okay but need faster.
Hire a) After disscusion finish with freelancer client can hire the freelancer for the specific project from Hire button (which is in Search Freelancer page) b) After a succesfully hired freelancer, freelancer name will be shown on the client Dashboard hired list | a) Done b) Done |  | all okay new point added : need to add a pop up for approe & disapprove
Make Offers a) After sent successfully hired in here client can see the sent offers list. | Done. Offer can be Accept or Reject from freelancer notification. |  | all okay new point added : need to add a pop up for approe & disapprove
Project Successfully complete then send rating to freelancer | I need to Ask @Madam about the page |  | Not done
Sample Test to assign new Freelancer |  | remove this , as of now no need , i will think about it latter | NA
Eye Icon Show Password | Done. |  | all okay
Coin Wallet | It is comopleted as per the database but not from both end
Ticketing System with Admin | Partly Done
Milestone Task wise | Done
New Message Notification | Working On
Project wise Report
Pyament History
Task Notification | Working On
Transfer payment (Admin) using Piyoner
Withdraw Payment using Piyoner
For Chat System (Freelancer and Client) use third party and customize this cometchat.com | Not Done, becase I got error.
Rehire Freelancer | Working On
Showing Proposal | Where to Show
Problem Ticket | Done (need to dispaly in admin)

## Freelancer
Full Fucntions | Arindam Comment | Client Comment | Testing Comment
Frelancer Login | Done. |  | all okay
a) Key List /All jobs (to search the project with all types of value) b) Need to fix some address,skills,budget etc | a) Done. b) Working On |  | partly done
a) Job Details Page (from where freelancer find the Submit Proposal button) b) Saved Job c) Flag This Job As an inappropriate d) Connects concept implementation e) Member since f) About Client g) Job Link | a) Done. b) Done. Need to display it somehere else.f) Done, g) Done |  | partly done
a) Submit Proposal b) Proposal Settings c) Job Details d) Terms | a) Done. b) Need clarification c) Done d) Done |  | partly done but display the full proposal.
Dashboard a) After succesfully submit the project will show on his Dashboard -> New Tab | a) Done. |  | all okay
Message a) After accepet the client notifiication in freelancer message box the speific client will shown.and they both can chat. | a) Done. Project Wise both can Chat Note: If freelancer accepts the offer but reject the hire proposal when given by client. Then what will happen in the messege box? |  | all okay need faster
Problem Ticket a) Done from freelancer end | a) Done (need to dispaly in admin) |  | partly done but display the full proposal.
- School | Need Clarification
- Past Projects (Task) | Need Clarification
- How Much Earn | Need discussion for implementation
- Mobile Number to Verify Code | Need SMS gateway
- About you | Done from freelancer BIO
- Account Holder Name, Bank Account | Not Done
- Email Verification | Server Issue
- Security Question | Need Clarification
- Messaging System [With Client] | Working
- New Message | Working
- Listing and Edit
- Past Task (Project) List
- Project Successfully complete then send rating to client
- Sample Test
- Ticketing System with Admin
- Milestone Task wise
- Earn report
- Change Password | Done
- Pyament History
- Task Notification
Wallet | a) Done as per database (need to fix the design) |  | partly done
- Withdraw payment using Piyoner
Edit Profile | a) Partialy done. Need to display the design wise |  | partly done
For Chat System (Freelancer and Client) use third party and customize this cometchat.com

## Admin
Full Fucntions | Arindam Comment | Client Comment | Testing Comment
Admin Login | Done. (admin@hirenwork.com / Admin@123) |  | all okay
Admin Module/Template/ | Done. |  | all okay
Manage Freelancer a) Listing b) Add c) Edit d) Delete | a) Done |  | partly done but need proper validation & need to work on delete
Manage Client a) Listing b) Add c) Edit d) Delete | a) Done |  | partly done but need proper validation & need to work on delete
Manage Category a) Listing b) Add c) Edit d) Delete | a) Done |  | all okay but delete not done.
Task list | a) Done |  | done but need to remove the project after 30 days of project post date , before delete the client gets notification last 5 days
- Posted Task [Export Csv/Delete]
- Assign Task
- Completed Task
- Closed Task
- Dispute Task
Wallet setting [Edit]
- Piyoner Setting
- Wallet Withdraw
Report
- Task wise Report
Manage Pages [Add/Edit/Delete]
Setting
- Social Setting
- Email Templates
- Commission Setting
Stats
- Transcation
- Task wise Transcation
- Freelancer / Client wise stats
Manage Admin [Add/Edit/Delete]
Manage Admin Roles [Add/Edit/Delete]
Manage Banner [Add/Edit/Delete]
Support Ticket
- Manage Category (Add/Edit/Delete)
- Ticket (View/Answer)
Manage Skill (Add/Edit/Delete)

## Front End
Full Fucntions | Arindam Comment | Client Comment | Testing Comment
FRONT DEVELOPMENT REQUIRE IN FREELANCER / CLIENT
Design Integate
Homepage
- Banner
- Category
- Home Blocks [Video, Content]
Member Login / Register / Forgot Password
- Member Login with Google+, Linkedin
- Member Register with Google+, Linkedin [Freelancer / Client]
- Frogot Password
Faq page
Contact Us
Password Validation required for Sign Up

## Full Site Task
ADMIN FUNCTIONALITY
Manage Freelancer [Add/Edit/Delete]
Manage Client [Add/Edit/Delete]
Manage Category [Add/Edit/Delete]
Manage Task [Add/Edit/Delete]
- Posted Task [Export Csv/Delete]
- Assign Task
- Completed Task
- Closed Task
- Dispute Task
Wallet setting [Edit]
- Piyoner Setting
- Wallet Withdraw
Report
- Task wise Report
Manage Pages [Add/Edit/Delete]
Setting
- Social Setting
- Email Templates
- Commission Setting
Stats
- Transcation
- Task wise Transcation
- Freelancer / Client wise stats
Manage Admin [Add/Edit/Delete]
Manage Admin Roles [Add/Edit/Delete]
Manage Banner [Add/Edit/Delete]
Support Ticket
- Manage Category (Add/Edit/Delete)
- Ticket (View/Answer)
Manage Skill (Add/Edit/Delete)
FREELANCER LOGIN
- Upload Profile Pic
- Add Skill, Experience
- School
- Past Projects (Task)
- How Much Earn
- Mobile Number to Verify Code
- About you
- Account Holder Name, Bank Account
- Email Verification
- Security Question
- Messaging System [With Client]
- New Message
- Listing and Edit
- Past Task (Project) List
- Project Successfully complete then send rating to client
- Sample Test
- Ticketing System with Admin
- Milestone Task wise
- Earn report
- Change Password
- Pyament History
- Task Notification
- Wallet
- Withdraw payment using Piyoner
- Edit Profile
For Chat System (Freelancer and Client) use third party and customize this cometchat.com
CLIENT LOGIN
- Edit Profile
- About / Portfolio
- Skill
- Verification Email / SMS
- Change Password
- Post Task (Project)
- Task (Project), Description, Location and Budget
- Thanks page
- My Task (Project)
- Task (Project) listing
- Review and Comment list
- Accept and Complete task
- Project Successfully complete then send rating to freelancer
- Sample Test to assign new Freelancer
- Ticketing System with Admin
- Milestone Task wise
- Messaging System [With Freelancer]
- New Message
- Listing and Edit
- Project wise Report
- Pyament History
- Task Notification
- Wallet
- Transfer payment (Admin) using Piyoner
- Withdraw Payment using Piyoner
For Chat System (Freelancer and Client) use third party and customize this cometchat.com
FRONT DEVELOPMENT REQUIRE IN FREELANCER / CLIENT
Design Integate
Homepage
- Banner
- Category
- Home Blocks [Video, Content]
Member Login / Register / Forgot Password
- Member Login with Google+, Linkedin
- Member Register with Google+, Linkedin [Freelancer / Client]
- Frogot Password
Faq page
Contact Us